SIMATS ENGINEERING (SAVEETHA SCHOOL OF ENGINEERING)

Department of Computer Science and Engineering

CO1 ASSESSMENT TOOL 2  –  Agile Sprint Planning & User Story Workshop

| Course Code: | CSA10 / CSA1004 | Course Title: | Software Engineering |
| --- | --- | --- | --- |
| CO Assessed: | CO1 | Assessment: | Assessment Tool 2 – Agile Sprint Planning & User Story Workshop |
| Weightage: | 20% | Total Marks: | 25 |
| CO1 Statement: | Apply advanced methodologies and agile project management techniques to manage software projects effectively |  |  |
| Student Name: | K Sreelatha | Reg. No.: | 192425248 |
| Date: | 13/10/2026 | Duration: | 60 minutes |

Code of Conduct I __K Sreelatha(192425248)______ (Name / Reg No) certify that this submission is my original work and that I have adhered to the guidelines specified for this assessment. I understand that any violation of academic integrity rules will result in disciplinary action. Signature of the Student: _____Sree K________

Annexure A – Agile Sprint Planning & User Story Workshop

Instructions to Students:

Each student is assigned an individual software project problem statement. Based on the given problem statement, perform an Agile Sprint Planning and User Story Workshop by applying Agile software engineering practices. Prepare a comprehensive sprint planning document covering the following aspects:

Based on the given problem statement, perform an Agile Sprint Planning and User Story Workshop by applying Agile software engineering practices. Prepare a comprehensive sprint planning document covering the following aspects:

- Identify the Project Vision and Stakeholders

  - Define the project's vision, objectives, and identify all key stakeholders involved.

- Create Epics and User Stories

  - Break down the requirements into Epics and formulate well-structured User Stories using the format:
As a <user>, I want <feature>, so that <benefit>.

- Define Acceptance Criteria

  - Write clear and measurable acceptance criteria for each selected user story using the Given–When–Then format or equivalent.

- Prioritize the Product Backlog

  - Organize and prioritize the product backlog based on business value, customer needs, and project dependencies.

- Plan the Sprint Backlog

  - Select high-priority user stories for the first sprint and divide them into actionable development tasks.

- Estimate Effort Using Story Points

  - Assign story points to each selected user story using an appropriate estimation technique (e.g., Fibonacci sequence or Planning Poker) and justify your estimates.

- Present the Sprint Goal and Expected Deliverables

  - Define a clear sprint goal and describe the expected sprint deliverables, including the features to be completed at the end of the sprint.

1. Project Vision

The vision of the Online Hotel Room Booking Website is to develop a user-friendly, secure, and responsive web application that enables customers to search for hotels, check room availability, book rooms, make payments, and manage their reservations online. The system also provides administrators with facilities to manage hotel rooms, prices, bookings, user accounts, and website information.

The website aims to simplify the hotel reservation process, reduce manual work, improve customer satisfaction, and provide convenient access through computers, tablets, and mobile devices.

2. Project Objectives

- Allow users to register, log in, and manage their profiles.

- Enable customers to search for rooms based on destination, dates, and number of guests.

- Display room types, prices, amenities, and availability.

- Allow users to book, modify, cancel, and view their booking history.

- Provide secure online payment facilities.

- Send booking confirmation emails to customers.

- Enable administrators to manage room quantities, prices, and reservations.

- Provide hotel information, contact details, customer service FAQs, local travel guides, and privacy policies.

- Develop a responsive website accessible on different devices.

3. Stakeholder Identification

| Stakeholder | Role and Responsibilities |
| --- | --- |
| Customers | Register, search rooms, book rooms, make payments, and manage reservations. |
| Administrator | Manage room details, prices, availability, bookings, and website content. |
| Hotel Management | Monitor reservations, room occupancy, revenue, and hotel operations. |
| Receptionist | Assist customers and verify booking details. |
| Development Team | Design, develop, test, and maintain the website. |
| Product Owner | Define requirements and prioritize the product backlog. |
| Scrum Master | Coordinate sprint activities and resolve development obstacles. |
| Payment Gateway Provider | Process online payments securely. |
| Email Service Provider | Send booking confirmations and notifications. |

4. Agile Methodology

The project follows the Scrum framework, an Agile software development approach. The project is divided into short development cycles called sprints. Each sprint produces a working part of the website.

The development team reviews progress at the end of each sprint, collects feedback, and makes improvements in subsequent sprints.

5. Identification of Epics

Epics represent large functional requirements that can be divided into smaller user stories.

| Epic ID | Epic Name | Description |
| --- | --- | --- |
| E1 | User Management | Registration, login, and profile management. |
| E2 | Room Search and Availability | Search hotels and check room availability. |
| E3 | Room Booking Management | Book rooms, view history, modify, and cancel bookings. |
| E4 | Payment and Notifications | Process payments and send booking confirmations. |
| E5 | Administrator Management | Manage rooms, prices, availability, and bookings. |
| E6 | Website Information Management | Manage hotel details, FAQs, contact information, travel guides, and privacy policies. |
| E7 | Reviews and Responsive Design | Allow customer reviews and support multiple devices. |

6. User Stories

User stories describe the required functionality from the user's perspective.

| Story ID | User Story | Priority |
| --- | --- | --- |
| US01 | As a customer, I want to register and log in so that I can access my account securely. | High |
| US02 | As a customer, I want to update my profile so that my personal information remains correct. | Medium |
| US03 | As a customer, I want to search for rooms by destination, dates, and guests so that I can find suitable accommodation. | High |
| US04 | As a customer, I want to check room availability so that I do not book an unavailable room. | High |
| US05 | As a customer, I want to book a room for specific dates so that I can reserve accommodation. | High |
| US06 | As a customer, I want to make online payments so that I can confirm my reservation. | High |
| US07 | As a customer, I want to view my booking history so that I can track previous and upcoming stays. | Medium |
| US08 | As a customer, I want to modify or cancel a booking at least three days before arrival so that I can manage changes to my travel plans. | Medium |
| US09 | As an administrator, I want to update room quantities and prices so that hotel information remains accurate. | High |
| US10 | As an administrator, I want to modify or cancel bookings so that I can manage reservations. | Medium |
| US11 | As an administrator, I want to update website information so that customers receive accurate hotel details. | Medium |
| US12 | As a customer, I want to receive confirmation emails and submit reviews so that I can verify my booking and share my experience. | Medium |

7. Acceptance Criteria

Acceptance criteria define the conditions that must be satisfied for a user story to be considered complete.

US01: User Registration and Login

Given that a customer visits the website,
When the customer enters valid registration details,
Then the system should create an account and allow the customer to log in using valid credentials.

US03: Search for Rooms

Given that a customer opens the room search page,
When the customer enters the destination, check-in date, check-out date, and number of guests,
Then the system should display suitable rooms with prices, amenities, and availability.

US04: Check Room Availability

Given that a customer selects a room and travel dates,
When the customer checks availability,
Then the system should display the available room quantity and prevent reservations exceeding the available inventory.

US05: Book a Room

Given that a customer is logged in and a room is available,
When the customer submits valid booking details,
Then the system should create a reservation and display its booking reference.

US06: Online Payment

Given that a customer has entered valid booking details,
When the customer completes payment through the integrated payment gateway,
Then the system should record the payment result and confirm the booking after successful payment.

US08: Modify or Cancel a Booking

Given that a customer has an existing reservation,
When the customer requests a modification or cancellation at least three days before arrival,
Then the system should permit the action according to the booking policy and update the reservation details.

If the request is made less than three days before arrival, the system should prevent the customer from modifying or cancelling the booking through the standard self-service option.

US09: Administrator Room Management

Given that an administrator is logged in,
When the administrator changes the quantity or price of any of the four room types,
Then the system should validate and save the updated information.

US10: Administrator Booking Management

Given that an administrator has valid access permissions,
When the administrator modifies or cancels a selected booking,
Then the system should update the reservation and maintain the correct booking status.

US11: Website Information Management

Given that an administrator is logged in,
When the administrator edits the room information, About Us, Contact Us, customer service FAQs, local travel and shipping guide, or privacy policy,
Then the system should save and display the updated information on the appropriate website page.

US12: Booking Confirmation

Given that a booking is successfully confirmed,
When the reservation is completed,
Then the system should send a confirmation email containing the booking reference, room details, dates, and payment information.

8. Product Backlog Prioritization

The product backlog contains all the features required for the website. Priorities are assigned according to business value, customer needs, and development dependencies.

| Priority | Story ID | Feature | Reason |
| --- | --- | --- | --- |
| 1 | US01 | User registration and login | Provides secure access. |
| 2 | US03 | Room search | Helps customers find accommodation. |
| 3 | US04 | Room availability | Prevents unavailable room bookings. |
| 4 | US05 | Room booking | Implements the main business function. |
| 5 | US06 | Online payment | Supports payment and booking confirmation. |
| 6 | US09 | Room and price management | Enables administrators to maintain inventory. |
| 7 | US07 | Booking history | Helps customers track reservations. |
| 8 | US08 | Modify and cancel bookings | Supports reservation changes. |
| 9 | US12 | Email confirmation and reviews | Improves customer communication and feedback. |
| 10 | US10 | Administrator booking management | Supports reservation administration. |
| 11 | US11 | Website information management | Keeps static content accurate. |
| 12 | US02 | Profile management | Allows customers to update personal information. |

9. Sprint Backlog – Sprint 1

Sprint Duration: 2 weeks

Sprint Goal: Develop the basic customer-facing functionality that enables users to register, log in, search for rooms, and check room availability.

Selected User Stories

| Story ID | Selected Feature | Story Points |
| --- | --- | --- |
| US01 | User registration and login | 5 |
| US03 | Room search | 5 |
| US04 | Room availability checking | 3 |
| Total |  | 13 |

Development Tasks

| Task ID | Development Task | Estimated Effort |
| --- | --- | --- |
| T1 | Design the registration and login pages. | 1 day |
| T2 | Implement user registration and authentication. | 2 days |
| T3 | Design the room search form. | 1 day |
| T4 | Implement destination, date, and guest search. | 2 days |
| T5 | Develop room availability checking. | 2 days |
| T6 | Test login, search, and availability functions. | 2 days |

The sprint backlog focuses on the essential features required before implementing the complete booking and payment workflow. The tasks are estimates and can be adjusted according to the team's capacity.

10. Story Point Estimation

Story points estimate the relative effort, complexity, and uncertainty of implementing a user story.

The team uses the Fibonacci sequence (1, 2, 3, 5, 8, 13) to estimate the effort required for each selected user story.

| User Story | Story Points | Justification |
| --- | --- | --- |
| US01: Registration and Login | 5 | Requires form validation, authentication, and account creation. |
| US03: Room Search | 5 | Requires search filters and display of matching rooms. |
| US04: Room Availability | 3 | Requires checking available inventory for selected dates. |
| Total | 13 |  |

The estimates are provisional and can be refined through Planning Poker, where team members discuss complexity and agree on a common estimate.

11. Sprint Goal

The goal of Sprint 1 is to develop a functional foundation for the Online Hotel Room Booking Website. At the end of the sprint, customers should be able to register, log in, search for hotels or rooms, and check room availability for selected dates.

12. Expected Sprint Deliverables

The expected deliverables at the end of Sprint 1 are:

- A working user registration page.

- A functional login page with input validation.

- A room search interface for destination, dates, and guests.

- A room availability checking feature.

- A basic room listing with prices and amenities.

- Test results for registration, login, search, and availability.

- A demonstration of the completed sprint features.

13. Future Sprint Plan

| Sprint | Planned Features |
| --- | --- |
| Sprint 2 | Room booking, booking form, and online payment integration. |
| Sprint 3 | Booking history, booking modification, cancellation, and confirmation emails. |
| Sprint 4 | Administrator room management, booking management, and user account management. |
| Sprint 5 | Static website information, customer service FAQs, local travel and shipping guide, privacy policy, reviews, ratings, and responsive design improvements. |

14. Conclusion

The Agile Sprint Planning and User Story Workshop provides a structured approach to developing the Online Hotel Room Booking Website. The project vision identifies the main objectives and stakeholders, while epics and user stories divide the requirements into manageable features.

Acceptance criteria define the expected behaviour of each feature. Product backlog prioritization helps the team focus on high-value requirements, and story point estimation supports realistic sprint planning.

By following the Scrum framework, the development team can deliver the website incrementally, test each feature, incorporate feedback, and improve the system throughout the development process.

Rubrics for Calculation

| Criteria | Excellent (5 Marks) | Good (3 Marks) | Satisfactory (2 Marks) | Needs Improvement (1 Mark) |
| --- | --- | --- | --- | --- |
| Project Vision & Stakeholder Identification (30%) | Project vision is clear, comprehensive, and aligned with the problem statement. All relevant stakeholders and their roles are correctly identified. | Vision is clear with minor omissions. Most stakeholders are correctly identified. | Vision is partially defined. Some stakeholders are missing or incorrectly identified. | Vision is unclear or incomplete. Stakeholders are poorly identified or missing. |
| Epics & User Stories (25%) | Epics are well-defined and user stories are complete, follow Agile format, and fully capture functional requirements. | Epics and user stories are mostly complete with minor formatting or requirement issues. | User stories are partially complete with limited Agile structure. | User stories are incomplete, unclear, or do not follow Agile practices. |
| Acceptance Criteria (20%) | Acceptance criteria are specific, measurable, testable, and aligned with all user stories. | Acceptance criteria are mostly clear and testable with minor gaps. | Acceptance criteria are partially defined and lack clarity or completeness. | Acceptance criteria are missing or not aligned with user stories. |
| Product Backlog Prioritization & Sprint Planning (15%) | Product backlog is logically prioritized, sprint backlog is realistic, and task breakdown is complete. | Backlog prioritization and sprint planning are mostly appropriate with minor issues. | Prioritization or sprint planning is partially complete with limited justification. | Backlog prioritization and sprint planning are poorly organized or incomplete. |
| Story Point Estimation, Sprint Goal & Presentation (10%) | Story point estimation is well justified, sprint goal is clear, deliverables are realistic, and presentation is professional and well organized. | Estimation and sprint goal are mostly appropriate with minor inconsistencies. Presentation is clear. | Estimation or sprint goal lacks justification. Presentation is adequate but incomplete. | Estimation is unrealistic or missing. Sprint goal, deliverables, and presentation are unclear or incomplete. |

| Criteria | Mark |
| --- | --- |
| Project Vision & Stakeholder Identification (30%) | /5 |
| Epics & User Stories (25%) | /5 |
| Acceptance Criteria (20%) | /5 |
| Product Backlog Prioritization & Sprint Planning (15%) | /5 |
| Story Point Estimation, Sprint Goal & Presentation (10%) | /5 |
| TOTAL | /25 |